## Cover
Cover
This Excel sheet contains information about the CESOP releases and supported XSD versions.
In case a sheet has been updated: - This sheet will be mentioned in the history; - The changes made since the last version will be highlighted in green.
Date | 2025-02-27
Status | Submitted for Information (SfI)
Version | 1.06
Author | SOFT-DEV
Public | DG TAXUD external
Confidentiality | Publicly available (PA)
History
Version | Date | Description
1.06 | 2025-02-27 | Introduction of the information related to CESOP intermediate release v1.6.2.
1.05 | 2024-11-15 | Adding the link of XSD User Guide v6.00.
1.04 | 2024-11-08 | Update of the release date of CESOP v1.6.0 in production and introducing the CESOP v1.7.0 release.
1.03 | 2024-10-30 | Update of the information related to the CESOP Validation Module v1.6.0 and of the release date of CESOP v1.6.0 in conformance.
1.02 | 2024-09-17 | Update of the expected PROD date of CESOP v1.6.0.
1.01 | 2024-08-19 | Update of the expected CONF and PROD dates of CESOP v1.6.0.
1.00 | 2024-07-19 | First version of the Excel.

## Releases, versions & dates
Mapping between XSD, XSD User Guide and CESOP (VM) releases versions
XML schema version | XSD User Guide version | CESOP release version and Validation Module | XSD version accepted by CESOP release and Validation Module
4.03 | 6.00 | 1.7.x | 4.02 - 4.03 |  | IMPORTANT NOTE: XSD Versions 4.00 and 4.01 will not be supported anymore as from CESOP v1.7.0.
4.03 | 5.00 | 1.6.x | 4.00 - 4.01 - 4.02 - 4.03
4.02 | 4.80 | 1.5.x | 4.00 - 4.01 - 4.02
4.02 | 4.61 | 1.4.x | 4.00 - 4.01 - 4.02
4.02 | 4.61 | 1.3.x | 4.00 - 4.01 - 4.02
4.02 | 4.40
4.01 | 4.20
4.00 | 4.00 | 1.2.x | 4.00
CESOP Central System versions
CESOP release version | Conformance Deployment Expected date (Member States Only) | Conformance Deployment Actual date (Member States Only) | Production Go Live Expected date | Production Go Live Actual date
1.7.0 | Q2 2025 | - | Q2 2025 | -
1.6.2 | 2025-04-10 | - | 2025-04-15 | -
1.6.0 | - | 2024-10-29 | - | 2024-11-06
1.5.0 | - | 2024-06-11 | - | 2024-06-18
CESOP Validation Module versions
Validation Module version | Validation Module User Manual version | CIRCABC link
1.7.0 | - | -
1.6.2 | 4.02 | CIRCABC link VM 1.6.2 - to be provided in beg. Of April 2025
1.6.0 | 4.00 | CIRCABC link VM 1.6.0
1.5.0 | 3.03 | CIRCABC link VM 1.5.0
1.4.5 | 3.02 | CIRCABC link VM 1.4.5
1.4.3 | 2.01 | CIRCABC link VM 1.4.3
1.3.0 | 2.01 | CIRCABC link VM 1.3.0